## QUESTIONS
QUESTIONS
.metadata in Github? Where does it come from and do we need it? Remove?
Databases - API...drawing - how to build API and where it should be between...
Backlog - go through
Server proposal - Chat, groups in DB's, file system, share location, share calendar...Sherlock Holmes (Harry)
Server protocol
Definition of Copy - Standard things in Android (Location / Google Maps)
XML - Expandable list. How to share XML, example Admin and Moderator

## Product Backlog
PRODUCT BACKLOG
Formula
ID | Feature | Prio | Business Value | Estimation Cost | Acceptance Test (DoD??)
26 | License (Define which license we should have) | 105 | 150 | 5
2 | App with simple gui (to test connect to server) | 85 | 150 | 15
3 | Connect to Server with app (incl. Protocol) | 80 | 150 | 30
1 | Create server application | 76.5 | 150 | 100
27 | Protocol | 72.3333 | 140 | 60
16 | Database (for users, groups etc...) | 68.85 | 135 | 100
4 | Lobby | 68.25 | 130 | 40
9 | Create user account | 68 | 120 | 15
21 | Admin and Moderator rights and functionality | 65.625 | 125 | 40
5 | Create group | 65 | 125 | 50
8 | Invite to groups (Search user and invite to group) | 43.2 | 80 | 25
10 | Edit user account | 35 | 50 | 5
7 | Request to join (Search group and send req. to join group) | 32.4 | 60 | 25
18 | Leave a group | 27.5 | 50 | 20
6 | Edit group | 22.6667 | 40 | 15
15 | Search users (server) | 17 | 30 | 15
20 | See other group members (list of users) | 11.3333 | 20 | 15
14 | Group Chat | 10.8 | 20 | 25
17 | Database for Harry Jokes | 3 | 2 | 1
22 | Moderator rights (reuse admin functionality) | 2.8 | 4 | 5
28 | A distibuted user manual in the application | 2 | 2 | 2
11 | Share files | 1.5375 | 3 | 80
19 | Game - not decided | 1.5 | 1 | 1
23 | Multiple clients for One User | 1.04 | 2 | 50
12 | Share location | 1.0299 | 2 | 67
24 | GUI Bling-Bling! (transparency in expandable list) | 0.56667 | 1 | 15
25 | User Authentication | 0.55 | 1 | 20
13 | Share calendar (export/import by user or iCal-links) | 0.51176 | 1 | 85
29
30
31
32
Note on C2: = ( [Business Value] / [Estimation Cost] ) + [Business Value] / 2

## Sprint Backlog
SPRINT BACKLOG
ID | WEEK | Feature | Business Value | E??? Cost | Acceptance Test (DoD??)
0
1 | [5 empty] | VECKA PER VECKA
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## Sprint Planning - 1
Activity
Server Setup | Server Setup | Michael
| Webserver | Mattias

## Sprint Planning - LV5
TO DO!!! - LV5
Activity | Description | Who
License | Beskriva licens, vilka som gäller....GPL, Apache... http://developer.android.com/guide/google/play/licensing/index.html | Harry
Remove from GitHub Repo | git rm för att ta bort tracking i repot och sen kan vi ta bort lokalt om filen inte ska finnas där alls eller om vi ska behålla de bara att de inte ska trackas. | Mattias
Protocol & Server | Connect to Server with app (incl. Protocol) | Anton, Michael
GUI - expandable list, changing views | Define GUI with menu and standard views and add onClick to be ready to for methods. | Stefan
Investigate Database on Webserver |  | Mattias